## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-07-j toasters
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Supporter I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | EH; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | EH; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | EH; 10/29/23 | Fail | There is no message - team 1A 11/13/23
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | EH; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | EH; 10/29/23 | Fail | we could not add the need to the funding basket from the main needs page, only once you click on the need do you see this option - team 1A 11/13/23
As a Supporter I want to see the details of a single need so I can add it to my funding basket. | Given that I am on the supporter Needs page when I choose a Need, then I can see the details. | Pass | BG; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am viewing a Need's details, when I want to add a need to my basket, then I can add a Need to my basket, and will navigate back to the Needs page. | Pass | BG; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am viewing a Need's details, when I want to don't want to a need to my basket, then I can go back to the needs page. | Pass | BG; 10/29/23 | Pass | you have a typo in this acceptance criteria - team 1A 11/13/23
As a Supporter I want to view my basket so that I choose what needs to support, and check out. | Given that I don't have any needs in my basket, when I choose to view my basket, then I see an error message telling me there's no needs in my basket, and I stay on the current page I was on. | Pass | BN; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am on the supporter funding basket page, when I choose to remove a Need, then it is removed from my cart. | Pass | BN; 10/29/23 | Pass | btw the need is removed from the cupboard when it is put into the cart, not just when you check out - team 1A 11/13/23
| Given that I am on the supporter funding basket page, when I choose to checkout my Needs, then they are all removed from my cart and needs cupboard, and I see a thank you message. | Pass | BN; 10/29/23 | Pass | team 1A 11/13/23
As a Supporter I want to search for specific needs so that I can find needs which fit what I'd like to contribute to better. | Given that I am on the supporter Needs page when there are needs in the cupboard with the query text, I can see the matching needs. | Pass | AA; 10/29/23 | Fail | search does not work. There is no button to search the text that was typed. -team 1A 11/13/23
| Given that I am on the supporter Needs page when there are not needs in the cupboard with the query text, I can not see any matching needs. | Pass | AA; 10/29/23 | Fail | search does not work. There is no button to search the text that was typed. -team 1A 11/13/23
As a admin I want to update Needs so that I don't need to delete then recreate needs with different details. | Given that I am on the admin need update page, when I choose to update the current Need, it will be updated and I'll be redirected back to the admin Needs page. | Pass | AA; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am on the admin need update page, when I don't want to update the current Need, I can go to the previous page I was on. | Pass | AA; 10/29/23 | Pass | team 1A 11/13/23
As a admin I want to delete Needs so that I can change my mind on Needs I don't want anymore. | Given that I am on the admin needs page, when I select the X next to a Need, then, that need will be removed from my cupboard. | Pass | EH; 10/29/23 | Pass | team 1A 11/13/23
As a admin I want to create Needs so that I can be funded for my projects. | Given that I am on the admin need create page, when I insert a need which isn't in the cupboard already, then that need will be added to the cupboard, and I will be sent to the needs page. | Pass | EH; 10/29/23 | Pass | we like that it goes back to the cupboard once you do this - team 1A 11/13/23
| Given that I am on the admin need create page, when I insert a need which is in the cupboard already, then I want to know this has happened, and stay on the creation page. | Pass | EH; 10/29/23 | Pass | team 1A 11/13/23
As a Supporter I want to login to the application so that I can do stuff. | Given that I am on the login page, when the username I insert is invalid, then I expect to know that the username is invalid. | Pass | BG; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am on the login page, when the username I insert is admin, then I expect to see the admin needs list. | Pass | BG; 10/29/23 | Pass | team 1A 11/13/23
| Given that I am on the login page, when the username I insert is not admin, then I expect to see the supporter needs list. | Pass | BG; 10/29/23 | Pass | team 1A 11/13/23
As a Supporter I want to logout so that people do not make unwanted changes for me. | Given that I am signed in or out, when I select the logout button then I expect to be signed out and see the login page. | Pass | AA; 10/29/23 | Pass | team 1A 11/13/23
As a Supporter I want the page to display my Supportername so that I know I am logged in | Given that I am signed in, when I view the page, then I expect to see my username at the top |  |  | Pass | team 1A 11/13/23
As a Supporter I want to fund partial needs so that I don’t need to supply whole need quantities. | Given that I am viewing the details of a need which is not in my basket when I change the desired quantity to a valid number then the desired amount will be added to basket and the cupboard will be updated. |  |  | Pass | team 1A 11/13/23
| Given that I am viewing the details of a need which is in my basket when I change the desired quantity to a valid number then the desired amount will be added to the basket and the cupboard will be updated. |  |  | Pass | team 1A 11/13/23
| Given that I am viewing the details of a need when I change the desired quantity to an invalid number then the need will not be updated in my cart or cupboard, and will display that the quantity is invalid. |  |  | Pass | team 1A 11/13/23
As a Supporter I want funded needs to be saved so that they can be tracked | Given a need is in the cart when I checkout then I expect the system to store a receipt of the needs I have checked out. |  |  | Pass | team 1A 11/13/23
As a Supporter I want to see who has funded the most expensive sum of needs so that there is competition in the application. | Given that I am on the leaderboard tab when there are supporters who have supported needs then I expect to see a sorted list of supporters on the leaderboard. |  |  | Pass | team 1A 11/13/23
| Giventhat I am on the leaderboard tab when there aren't supporters who have supported needs then I expect not to see any supporters there. |  |  | Pass | EH; 11/13/2023
As an admin I want to view all the past receipts so that I can keep track of past funding. | Given that I am an admin when I click on my "funded needs" tab then I can view all past orders from supporters. |  |  | Pass | team 1A 11/13/23
| Given that I am an admin and have selected a funded need, when I choose to send a message to the user, and have typed a message, the message will be sent so that I can thank the supporter. |  |  | Pass | this is fun! - team 1A 11/13/23
As a potential supporter I want to create an account so that I can become a supporter. | Given that I am not a signed-up user when I am in the login page, then I expect to be able to create an account with a specified username. |  |  | Pass | team 1A 11/13/23
| Given that I enter an existing username when I select the "sign up" button, then I expect to see an error telling me that the user already exists |  |  | Pass | team 1A 11/13/23